## TestPlan
TestPlan
Item | Details
Project Name | Scambuster - Media Domain Validation
Objective | To validate Scambuster app media links for scam/safe detection & functionality
Team Size | 5 Members (Enterprise Crowd Model)
Scope IN | Link Validation (Media), Post Sharing, Search, Login
Scope OUT | Payment, Admin Panel
Environment | Android 12,13, iOS, Chrome v120, Excel/Sheets, JIRA
Roles | Member 1 Dharshini: QA Tester - 70 URLs Validation + 16 Test Cases | Member 2: 70 URLs Functional | Member 3: UI/Compatibility | Member 4: Retest/Regression | Member 5: Bug Reports & Docs
Entry Criteria | Requirements ready, Test data (350 links) ready
Exit Criteria | 90% cases executed, Critical bugs closed, Summary ready
Risks | If URL server down, testing blocked
Schedule | Day1 Req Analysis, Day2 Test Plan, Day3-4 Test Cases, Day5 Execution, Day6 Closure

## TestCases Mainsheet
TestCases - Main sheet - 16+ cases (Rare case included)
Test ID | Module | Type | Scenario | Steps | Expected result | Status
TC_01 | Login | Positive | Valid login | Enter valid creds -> login | Dashboard should open | Pass
TC_02 | Login | Negative | Invalid login | Wrong password | Error message | Pass
TC_03 | Media Link | Positive | Valid safe media link | Paste hindu.com news link -> Check | Show SAFE - Green | Pass
TC_04 | Media Link | Negative | Empty link | Click check without link | Enter link error | Pass
TC_05 | Media Link | Negative | Invalid format | Paste htp://abc | Invalid link error | Pass
TC_06 | Media Link | Rare | 500+ char long media URL | Paste 500 char link -> Check | Should not crash, show error | Pass
TC_07 | Media Link | Rare | Same link twice fast | Paste same link 2 times quickly | Should not duplicate | Pass
TC_08 | Media Link | Rare | Emoji in media link | Paste timesofindia.com😂 | Invalid error gracefully | Pass
TC_09 | Media Link | Rare | Internet OFF + Check | OFF internet -> Click Check | No internet message | Pass
TC_10 | Media Link | Rare | Minimize & reopen | Paste link -> minimize app -> open | Link should persist | Pass
TC_11 | Media Link | Rare | 10 links fast check | Check 10 links continuously | App should not crash | Pass
TC_12 | Media Link | Rare | Special chars @@@@ | Paste @@@@ link | Invalid error | Pass
TC_13 | Media Link | Rare | Expired news link 2020 | Paste old 2020 news link | Show expired/warning | Pass
TC_14 | Post Share | Positive | Share valid media post | Share after validation | Share success | Pass
TC_15 | UI | UI | Button alignment & spelling | Check all pages | No UI issues | Pass
TC_16 | Compatability | Compatability | Android 12 vs 13 | Run TC_03 in both | Same result | Pass

## Execution Results
Execution Results
URL_ID | URL_Type | Expected_Result | Actual_Result | Status | Remarks
URL_01 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_02 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_03 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_04 | Scam | SCAM - Red | SCAM shown | Pass | No Bug
URL_05 | Scam | SCAM - Red | SCAM shown | Pass | No Bug
URL_06 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_07 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_08 | Scam | SCAM - Red | SCAM shown | Pass | No Bug
URL_09 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_10 | Safe | SAFE - Green | SAFE shown | Pass | No Bug
URL_11 to URL_70 | Safe/Scam Mix | Correct Label | Correct Label Shown | Pass | No Bug - App Stable
Final Summary: Total URLs Tested by Me:70 Pass: 70 Fail: 0 Critical Bugs: 0 - No Bugs Found App Status: Stable - Ready to Release Note: Team total 350 URLs (5 members x 70). Certificate 29/05/2026.

## RTM + Summary
RTM
Requirement | Test Cases | Coverage
REQ_01 Login should work | TC_01, TC_02 | Covered
REQ_02 Media link | TC_03 to TC_13 | Covered (Rare cases)
REQ_03 Post sharing | TC_14 | Covered
REQ_04 UI clean | TC_15 | Covered
REQ_05 Compatibility | TC_16 | Covered
Summary
Metric | Value
Total Test Cases | 16
Passed | 16
Failed | 0
Total Bugs | 0 No Critical Bugs Found
Bugs Closed | 0
Bugs Open | 0
Team | 5 Members
Certificate | Awarded 29/05/2026 by GG Sagar
App Status | Stable - Ready to Release